## Schedule
Task# | Description | Start Date | End Date | Duration in Days | Days Passed | Days Left | Effort Hours Estimate | Effort Hours Complete | Effort Hours Left | Input | Output | Responsible | Status
| Total --> |  |  | 281 | 55 | 0 | 83 | 83 | 0
001 | Project Start and End Dates | 2021-06-07 | 2021-08-01 | 55
002 | Training Cole on GIt and Jira | 2021-06-26 | 2021-06-26 | 0 |  |  | 2 | 2 | 0 | Jira | Trained Cole (RIS-5 Jira Issue) | Zach(Owner) | Complete
003 | Brainstorm and Add tasks to schedule | 2021-06-26 | 2021-06-27 | 1 |  |  | 5 | 5 | 0 | Schedule Excel Sheet | Team Schedule for Project | All | Complete
004 | Import Team 8 Project into Github | 2021-06-26 | 2021-06-28 | 2 |  |  | 1 | 1 | 0 | Team 8 Project Files | Github Created https://github.com/zcmace/RIS-Project | Zach(Owner) | Complete
005 | Train Andrew on Git and Jira | 2021-06-27 | 2021-06-29 | 2 |  |  | 1 | 1 | 0 | Jira | Trained Andrew (RIS-14 bug) | Zach(Owner) | Complete
006 | Setup SQL server so all can access it | 2021-06-30 | 2021-06-30 | 0 |  |  | 3 | 3 | 0 | SQL Installation Files | Working MySQL Database | Zach(Owner) | Complete
007 | Understand Project Files and Application | 2021-06-30 | 2021-07-01 | 1 |  |  | 4 | 4 | 0 | Github Application Files |  | All | Complete
008 | Debug Sign-On system | 2021-06-30 | 2021-07-02 | 2 |  |  | 3 | 3 | 0 | VScode, WebSecurityConfig.java | Problem fixed in WebSecurityConfig.java | Zach(Owner) | Complete
008a | find sign on point in Java security files | 2021-06-30 | 2021-07-03 | 3 |  |  | 1 | 1 | 0 | VScode | WebSecurityConfig.java | Zach(Owner) | Complete
009 | Indentify Possible Features | 2021-06-30 | 2021-07-04 | 4 |  |  | 2 | 2 | 0 | VScode, User Manual, RIS Slides | Identified Two Possible Features | Kevin F(owner), | Complete
010 | Get approval for features | 2021-06-30 | 2021-07-05 | 5 |  |  | 1 | 1 | 0 | Possible Features List, Feature Proposals | Approved Features | Zach(Owner) | Complete
011 | Design and Implement billing | 2021-07-07 | 2021-07-14 | 7 |  |  | 4 | 4 | 0 | Modeling Tool, Feature UML diagram | Implemented Feature and Java files | Andrew(owner) | Complete
012 | Test billing | 2021-07-14 | 2021-07-21 | 7 |  |  | 2 | 2 | 0 | Feature 1 Unit Tests | tested feature functionality | Andrew(owner) | Complete
013 | Deliver billing feature | 2021-07-21 | 2021-07-30 | 9 |  |  | 1 | 1 | 0 | Vscode, Git Feature 1 Branch | fully integrated Feature | Andrew(owner) | Complete
|  |  |  | 0 |  |  |  |  | 0
015 | Design and Implement User_info panel | 2021-07-07 | 2021-07-14 | 7 |  |  | 4 | 4 | 0 | Modeling Tool, Feature UML diagram | Implemented Feature and Java files | Cole(owner), Kevin F | Complete
016 | Test user_info.html | 2021-07-14 | 2021-07-21 | 7 |  |  | 2 | 2 | 0 | Feature 2 Unit Tests | tested feature functionality | Cole(owner), Kevin F | Complete
017 | Deliver User_info feature | 2021-07-21 | 2021-07-30 | 9 |  |  | 1 | 1 | 0 | Vscode, Git Feature 2 Branch | fully integrated Feature | Cole(owner), Kevin F | Complete
018 | Debug Admin Dashboard | 2021-07-05 | 2021-07-14 | 9 |  |  | 3 | 3 | 0 | VScode, AdminController.java | AdminController.java | Andrew(owner) | Complete
019 | Debug Radiologists Dashboard | 2021-07-05 | 2021-07-14 | 9 |  |  | 3 | 3 | 0 | Vscode, RadiologistController.java | working radio dashboard | Cole(owner) | Complete
020 | Debug Referral MD dashboard | 2021-07-07 | 2021-07-14 | 7 |  |  | 3 | 3 | 0 | referral_md.java | working referral_md dashboard | Zach(Owner) | Complete
021 | Debug Technician Dashboard | 2021-07-07 | 2021-07-14 | 7 |  |  | 3 | 3 | 0 | technicialController.java, | working technician dashboard | Zach(Owner) | Complete
022 | Debug Receptionists Dashboard | 2021-07-07 | 2021-07-14 | 7 |  |  | 3 | 3 | 0 | receptionistController.java | working receptionist dashboard | Kevin F(owner), | Complete
023 | Test Admin Features | 2021-07-14 | 2021-07-21 | 7 |  |  | 3 | 3 | 0 | Test conditions for Admin | fully tested admin functionality | Andrew(owner) | Complete
024 | Test Radiologists Features | 2021-07-14 | 2021-07-21 | 7 |  |  | 3 | 3 | 0 | Test conditions for Radiologist | fully tested radiologists functionality | Cole(owner) | Complete
025 | Test Referral MD Features | 2021-07-14 | 2021-07-21 | 7 |  |  | 3 | 3 | 0 | Test conditions for Referral_MD | full tested referral md functionality | Zach(Owner) | Complete
026 | Test Technician Features | 2021-07-14 | 2021-07-21 | 7 |  |  | 3 | 3 | 0 | Test conditions for Technician | fully tested technician functionality | Kevin F(owner) | Complete
027 | Test Receptionists Features | 2021-07-14 | 2021-07-21 | 7 |  |  | 3 | 3 | 0 | Test conditions for Receptionist | fully tested receptionist functionality | Cole(owner) | Complete
028 | Maintain Jira | 2021-06-30 | 2021-08-01 | 32 |  |  | 5 | 5 | 0 | Schedule Document, Jira Dashboard | Organized projectManagment | Zach(Owner) | Complete
029 | Presentation Slides | 2021-07-21 | 2021-07-30 | 9 |  |  | 2 | 2 | 0 | Project grading rubric and example slides | Personalized slides that demonstrate our project | Kevin F(owner) | Complete
030 | Update System Models | 2021-07-21 | 2021-07-30 | 9 |  |  | 2 | 2 | 0 | Old system model diagrams and new feature models | integrated models into one document | Kevin F(owner), Zach | Complete
031 | Update Supplementary Diagrams | 2021-07-21 | 2021-07-30 | 9 |  |  | 2 | 2 | 0 | Old supplementary diagrams and new feature diagrams | integrated diagrams | Andrew(owner) | Complete
032 | Update User Manual | 2021-07-21 | 2021-07-30 | 9 |  |  | 1 | 1 | 0 | new feature usage, old user manual | complete and efficient user manual | Cole(owner), Andrew | Complete
033 | Update Installation Instructions | 2021-07-21 | 2021-07-30 | 9 |  |  | 1 | 1 | 0 | old installation instructions, bug fixes | Working installation manual | Zach(Owner), Cole | Complete
034 | Create Lessons Learned Document | 2021-07-21 | 2021-07-30 | 9 |  |  | 3 | 3 | 0 | Collective Experiences, Meeting Minutes | Finished Lessons Learned Document | Zach(Owner), All | Complete
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
Formulas:
Days Passed = TODAY() -[Start Date, row below]
Days Left = [End Date, row below]-TODAY()