## Schedule
Task# | Description | Start Date | End Date | Duration in Days | Days Passed | Days Left | Effort Hours Estimate | Effort Hours Complete | Effort Hours Left | Input | Output | Responsible | Status
| Total --> |  |  | 976 | 61 | 1 | 252 | 252 | 0
001 | Project Start and End Dates | 2021-02-10 | 2021-04-13 | 62
002 | Investigate RIS Requirements | 2021-02-10 | 2021-02-23 | 13 |  |  | 10 | 10 | 0 |  |  | All Members | Complete
003 | Learn Jira Interface | 2021-02-10 | 2021-02-23 | 13 |  |  | 4 | 4 | 0 |  |  | All Members | Complete
004 | Setup Github Repository | 2021-02-10 | 2021-02-23 | 13 |  |  | 1 | 1 | 0 |  |  | All Members | Complete
005a | Breakdown Project Requirements | 2021-02-24 | 2021-02-26 | 2 |  |  | 2 | 2 | 0 |  |  | All Members | Complete
005b | Assign Project Goals | 2021-02-24 | 2021-02-26 | 2 |  |  | 2 | 2 | 0 |  |  | All Members | Complete
005c | Setup Development Environments | 2021-02-24 | 2021-02-25 | 1 |  |  | 3 | 3 | 0 | VSCode, XAMPP, Cpanel |  | Seth Nurmi, All Members | Complete
006 | Produce Diagrams (Java Class Diagram, Entity Relationship Diagram, Process Flow Chart) | 2021-03-04 | 2021-03-11 | 7 |  |  | 3 | 3 | 0 | See above |  | Seth Nurmi | Complete
007 | Develop Java Classes / Class Diagrams | 2021-03-04 | 2021-03-11 | 7 |  |  | 10 | 10 | 0 | Java classes must have all instance variables listed in the Java class diagram. All classes must have appropriate getter and setter methods (getVariable, setVariable, variable first letter must be capitalized). | All primary and secondary java classes | Seth Nurmi - John, Aaron | Complete
007a | Primary Classes | 2021-03-12 | 2021-03-16 | 4 |  |  | 4 | 4 | 0 | Refer to Java class diagram for requirements | User.java, Patient.java, Order.java, Appointment.java, ImagingInfo.java, DiagnosticReport.java | Seth Nurmi - John, Aaron | Complete
007b | Secondary Classes | 2021-03-12 | 2021-03-16 | 4 |  |  | 2 | 2 | 0 | Refer to Java class diagram for requirements | Roles.java, Alert.java, Status.java, Modality.java | Seth Nurmi - John, Aaron | Complete
008 | Develop User Interface | 2021-03-08 | 2021-03-26 | 18 |  |  | 20 | 20 | 0 | Refer to Process Flow Chart for required views and forms. Forms must use ThymeLeaf object parsing with Java class models. |  |  | Complete
009 | Develop Login Page | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Process Flow Chart | login.html |  | Complete
010 | Develop User Roles and Permissions | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Java Class Diagram | Roles.java, Alert.java, Status.java, Modality.java |  | Complete
|  |  |  | 0 |  |  | 0 | 0 | 0
012 | Develop MD Referral Dashboard | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Process Flow Chart | home.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
013 | Develop New Patient Form | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Java Class Diagram | referral_index.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
014 | Develop Patient Lookup Tool | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Process Flow Chart | referral_index.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
015 | Develop Patient Content View (All Patients) | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Java Class Diagram | referral_index.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
016 | Develop New Order Form | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Java Class Diagram | referral_index.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
017 | Develop Order Content View (All Orders, Specific Order) | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Java Class Diagram | orders.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
018 | Develop Diagnostic Content View (Specific Report) | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Java Class Diagram | diagnostic_form.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
019 | Develop Receptionist Dashboard | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Process Flow Chart | home.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
020 | Develop New/Modify Appointment Form | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Java Class Diagram | appointment_form.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
021 | Develop Appointment Content View (All Appointments, Today's Appointments) | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Java Class Diagram | order_form.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
022 | Develop Order Content View (Unscheduled Orders) | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Process Flow Chart | home.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
023 | Develop Patient Check-In View | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Process Flow Chart | home.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
024 | Develop Technician Dashboard | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Process Flow Chart | home.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
025 | Develop Appointment Content View (Checked-In) | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Java Class Diagram | appointments.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
026 | Develop New/Modify Imaging Info Form | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Java Class Diagram | imaging_form.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
027 | Develop Imaging Info Content View (Specific Imaging Info) | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Java Class Diagram | imaging_form.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
028 | Develop Radiologist Dashboard | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Process Flow Chart | home.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
029 | Develop Order Content View (Imaging Complete Orders) | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Java Class Diagram | orders.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
030 | Develop New/Modify Diagnostic Report Form | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Java Class Diagram | diagnostic_form.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
031 | Develop Diagnostic Content View (Specific Report) | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Java Class Diagram | order_overview.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
032 | Develop Admin Dashboard | 2021-03-08 | 2021-03-26 | 18 |  |  | 10 | 10 | 0 | Java Class Diagram | admin_dashboard.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
033 | Develop System Users Content View (All) | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Java Class Diagram | admin_dashboard.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
034 | Develop New/Modify System Users Form | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Java Class Diagram | admin_dashboard.html | Seth Nurmi - Seth, Alyssa, Brendan | Complete
035 | Develop Modalities Content View (All) | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Java Class Diagram |  | Seth Nurmi - Seth, Alyssa, Brendan | Complete
036 | Develop New/Modify Modalities Form | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Java Class Diagram |  | Seth Nurmi - Seth, Alyssa, Brendan | Complete
037 | Develop Patient Alerts Content View (All) | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Java Class Diagram |  | Seth Nurmi - Seth, Alyssa, Brendan | Complete
038 | Develop New/Modify Patient Alerts/Form | 2021-03-08 | 2021-03-26 | 18 |  |  | 3 | 3 | 0 | Java Class Diagram |  | Seth Nurmi - Seth, Alyssa, Brendan | Complete
039 | Develop Referral MD Controller | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Process Flow Chart | ReferralMDController.java | Seth Nurmi - Seth, Brendan | Complete
040 | Develop Referral MD Data Objects | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Java Class Diagram | Various Java classes | Seth Nurmi - Seth, Brendan | Complete
041 | Develop Receptionist Controller | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Process Flow Chart | ReceptionistController.java | Seth Nurmi - Seth, Brendan | Complete
042 | Develop Receptionist Data Objects | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Java Class Diagram | Various Java classes | Seth Nurmi - Seth, Brendan | Complete
043 | Develop Technician Controller | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Process Flow Chart | TechnicianController.java | Seth Nurmi - Seth, Brendan | Complete
044 | Develop Technician Data Objects | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Java Class Diagram | Various Java classes | Seth Nurmi - Seth, Brendan | Complete
045 | Develop Radiologist Controller | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Process Flow Chart | RadiologistController.java | Seth Nurmi - Seth, Brendan | Complete
046 | Develop Radiologist Data Objects | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Java Class Diagram | Various Java classes | Seth Nurmi - Seth, Brendan | Complete
047 | Develop File Upload System | 2021-03-08 | 2021-03-26 | 18 |  |  | 5 | 5 | 0 | Process Flow Chart | Various Java classes | Seth Nurmi - All members | Complete
048 | Develop Schedule Conflict System | 2021-03-08 | 2021-03-26 | 18 |  |  | 10 | 10 | 0 | Process Flow Chart | Various Java classes | Seth Nurmi - All members | Complete
049 | Develop Test Cases | 2021-03-26 | 2021-04-11 | 16 |  |  | 2 | 2 | 0 | Process Flow Chart | Test Case Diagram | Seth Nurmi - All members | Complete
050 | Produce Test Case Results | 2021-03-26 | 2021-04-11 | 16 |  |  | 2 | 2 | 0 | Process Flow Chart | Test Case Diagram | Seth Nurmi - All members | Complete
051 | Identify Bugs | 2021-03-26 | 2021-04-11 | 16 |  |  | 5 | 5 | 0 | RIS System | RIS System | Seth Nurmi - All members | Complete
052 | Debug System | 2021-03-26 | 2021-04-11 | 16 |  |  | 10 | 10 | 0 | RIS System | RIS System | Seth Nurmi - All members | Complete
053 | Develop Detailed Installation Instructions | 2021-03-26 | 2021-04-11 | 16 |  |  | 3 | 3 | 0 | Project Deliverables: ERD, Java Class Diagram, Flow Chart, | Installation Instructions | Seth Nurmi - All members | Complete
054 | Compile List of Tool and Resources | 2021-03-26 | 2021-04-11 | 16 |  |  | 2 | 2 | 0 | Project Deliverables: ERD, Java Class Diagram, Flow Chart, | List of Tools and Resources | Seth Nurmi - All members | Complete
055 | Produce User Manual | 2021-03-26 | 2021-04-11 | 16 |  |  | 2 | 2 | 0 | Project Deliverables: ERD, Java Class Diagram, Flow Chart, | User Manual | Seth Nurmi - All members | Complete
056 | Produce Project Deliverables Document | 2021-03-26 | 2021-04-11 | 16 |  |  | 2 | 2 | 0 | Project Deliverables: ERD, Java Class Diagram, Flow Chart, | Project Deliverables Document | Seth Nurmi - All members | Complete
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
Formulas:
Days Passed = TODAY() -[Start Date, row below]
Days Left = [End Date, row below]-TODAY()

## Group Member Tasks
Java Class Tasks | Notes | Responsible | Done | Front End - Form Tasks | Notes | Responsible | Done | Front End - Content View Tasks | Notes | Responsible | Done | Back End - Controllers | Notes | Responsible | Done | Back End - Data Objects | Notes | Responsible | Done
Create primary java classes | Create java classes with all required instance variables. Check the Java Class Diagram for requirements. | Aaron, John | x | Create New/Modify Patient Form | Must use ThymeLeaf form parsing objects. Input data can be found in Java class diagram | Alyssa, Brendan, Seth | x | Create View Patients Table | Format Appropriately so that the DataTables JavaScript library can be applied to them. This means that tables should have appropriate structure (table head and table body, etc.) | Alyssa, Brendan, Seth | x | Develop User Controller | Handle login/logout, and allow users to change password | Seth, Brendan | x | Create User table and associated tables (Roles) | Refer to Entity Relationship Diagram for table columns | Seth, Brendan | x
Create secondary java classes | All instance variables need getter/setter methods | Aaron, John | x | Create New/Modify Order Form |  | Alyssa, Brendan, Seth | x | Create View Orders Table |  | Alyssa, Brendan, Seth | x | Develop Admin Controller | Handle admin forms/views | Seth, Brendan | x | Create Patient table and associated tables (Patient Alerts) |  | Seth, Brendan | x
Create all required getter/setter methods | Getter and Setter methods follow format getVariable_name() where the first letter of the variable is capitalized | Aaron, John | x | Create New/Modify Appointment Form |  | Alyssa, Brendan, Seth | x | Create View Appointments Table |  | Alyssa, Brendan, Seth | x | Develop ReferralMD Controller | Handles patient lookup/ creation, order creation, order viewing, diagnostic report viewing | Seth, Brendan | x | Create Order table and associated tables (Modalities) |  | Seth, Brendan | x
|  |  |  | Create New/Modify Imaging Info Form |  | Alyssa, Brendan, Seth | x | Create View Imaging Info Table |  | Alyssa, Brendan, Seth | x | Develop Receptionist Controller | Handles appointment creation/modifying/viewing, order viewing | Seth, Brendan | x | Create Appointment table |  | Seth, Brendan | x
|  |  |  | Create New/Modify Diagnostic Report Form |  | Alyssa, Brendan, Seth | x | Create View Diagnostic Report Table |  | Alyssa, Brendan, Seth | x | Develop Technician Controller | Handles imaging info creation/modifying/viewing, order viewing, appointment viewing, order status updating | Seth, Brendan | x | Create Imaging info table |  | Seth, Brendan | x
|  |  |  | Create New/Modify System User Form |  | Alyssa, Brendan, Seth | x | Create View System Users Table |  | Alyssa, Brendan, Seth | x | Develop Radiologist Controller | Handles diagnostic report creation/modifying/viewing, appointment viewing, order viewing, order status updating | Seth, Brendan | x | Create Diagnostic report table |  | Seth, Brendan | x
|  |  |  | Create New/Modify Modalities Form |  | Alyssa, Brendan, Seth | x | Create View Modalities Table |  | Alyssa, Brendan, Seth | x
|  |  |  | Create New/Modify Patient Alerts Form |  | Alyssa, Brendan, Seth | x | Create View Patient Alerts Table |  | Alyssa, Brendan, Seth | x
[8 empty] | Create View Single Entry - Patient | Similar format to form, perhaps use same inputs set to readonly | Alyssa, Brendan, Seth | x
[8 empty] | Create View Single Entry - Order |  | Alyssa, Brendan, Seth | x
[8 empty] | Create View Single Entry - Appointment |  | Alyssa, Brendan, Seth | x
[8 empty] | Create View Single Entry - Imaging Info |  | Alyssa, Brendan, Seth | x
[8 empty] | Create View Single Entry - Diagnostic Report |  | Alyssa, Brendan, Seth | x